## Activity Log
Name: |  | Project Group (Name/Number): Group 2
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2023-05-03 | Had a meeting to decide on our topic, chose adult female literacy rates. | 1 hour 30 mins | Yes | We have a meeting notes google doc including what was discussed.
7 | 2023-05-05 | Second meeting, allocated roles and variables to research and to find databases for. | 45 minutes | Yes | Refined the project objective - We decided to look at the five countries with the highest adult female literacy rates and the five countries with the lowest adult female literacy rates, and compare the literacy rates against other variables.
8 | 2023-05-08 | Data cleaning (literacy dataset) | 4 hours | No | Emi and Natalie - started cleaning the adult literacy dataset.
8 | 2023-05-08 | Debugging/GitHub (literacy dataset) | Approximately 1 hour | Yes | Natalie - Went through the first literacy data cleaning session and debugged problem. Set up group GitHub.
8 | 2023-05-09 | Data cleaning (literacy dataset) | 2 hours | No | Emi and Natalie - Continued cleaning the female literacy dataset
8 | 2023-05-09 | Data cleaning (literacy dataset) | 2.5 hours | Yes | Natalie - Worked on the data cleaning for the literacy dataset and tidied up the Jupyter Notebook by adding markdowns to explain each step of the data cleaning process.
8 | 2023-05-10 | Data cleaning/visualisation production (literacy dataset) | 2 hours | No | Emi and Natalie - Checked final clean dataset and produced some visualisations.
8 | 2023-05-10 | Visualisation production (literacy dataset) | 1 hour | Yes | Natalie - Finished tidying up the visualisations for the adult female literacy dataset, pushed to GitHub, opened a PR - Emi as reviewer
8 | 2023-05-10 | Third meeting showing the team the cleaned dataset | 1 hour | Yes | Group - We showed the cleaned dataset to the rest of the team, discussed other factors to include & how to approach group homewok
8 | 2023-05-10 | Data cleaning (government ependiture dataset) | 3 hour | Yes | Rhianna - cleaning the dataset, merging incomplete data, finding the mean and median
8 | 2023-05-10 | Additional dataset | 30 mins | Yes | Emi and Natalie searched for & downloaded more dataset to include in analysis.
8 | 2023-05-12 | Worked on the group homework | 1.5 hours | No | Emi and Rhianna started the group homework
8 | 2023-05-14 | Worked on the group homework | Approximately 10 mins | No | Natalie - Added to the group homework
8 | 2023-05-15 | Worked on the group homework | 15 mins | No | Lilia- Added some points to the group homework
9 | 2023-05-15 | worked on API data | 1hour | No | Emi worked on reading API dataset
9 | 2023-05-15 | Data cleaning discussion | 1 hour | Yes | Emi and Natalie - discussed APIs, potential variables, and assigned tasks (Natalie to clean child marriage dataset, Emi to work on API data)
9 | 2023-05-15 | Group meet-up after class | 1 hour | Yes | Rhianna, Natalie, Lilia, Kayla - Finished the few last bits of our homework, decided on our variables.
9 | 2023-05-15 | Preparing to submit hw via GitHub | 1 hour | Yes | Natalie - Sorted out the homework on GitHub, opened a PR.
9 | 2023-05-16 | Preparing GPI data for exploration using SQL | 30 mins | Yes | Lilia
9 | 2023-05-16 | Cleaned child marriage dataset, merged clean dataset with clean literacy dataset, created visualisations | 4 hrs 55 mins | Yes | Natalie - Started and finished cleaning child marriage dataset. Merged with clean literacy table. Created a bar chart. Created a PR on GitHub.
9 | 2023-05-16 | Going through API dataset and converting to JSON | 1 hour | No | Emi - converted the api data to json file
9 | 2023-05-16 | Group meet-up | 1 | No | Group - worked on the API, discussed what we have done since last meet-up
9 | 2023-05-17 | Worked on API and started income group data cleaning | 1 hr 50 | Yes - API works, No - data cleaning unfinished | Emi, Rhianna, Natalie - worked on API
9 | 2023-05-18 | Checking female literacy data | 1 | Maybe? | Natalie - checked female literacy dataset to see if mean was appropriate to use
9 | 2023-05-18 | Finishing the JSON file & adding to female literacy data | 1 hour | Yes | Emi completed the json file & added it to the female lit & child marriage table
8 | 2023-05-18 | Tidied up literacy and child marriage datasets | 1 hour | No | Natalie - Investigated whether the mean or median would be better to use for the child marriage dataset.
9 | 2023-05-19 | Checking datasets | 30 mins | Yes | Natalie and Emi - Determined whether the median or mean is better for the child marriage dataset.
9 | 2023-05-20 | Group meet-up | 1 hour | Yes | Group meet-up - Went over the cleaned data, assigned tasks for the last week.
9 | 2023-05-20 | Presentation | 1 hour | No | Natalie - Found a template for the presentation and editing/adding information to the slides
9 | 2023-05-20 | GPI-data + merging all (prepareing final dataset to run regression on) | 1 hour | No | Lilia-analysing and merging all the data available in github
9 | 2023-05-21 | Finding out how to run a regression in Python | 2 hours | No | Lilia
10 | 2023-05-22 | Running regression on our data using python | 2 hours | Yes | Lilia
10 | 2023-05-22 | Created the Project Report, documenting the process for the project and steps taken, as well as any challenges. Presented to the group to determine any additions needed. | 2.5 hours | Yes | Befru - presented to the group in the next meeting to edit as needed.
10 | 2023-05-22 | Finalising literacy and child marriage notebooks | Approximately 4 hours | Yes | Natalie - Finalised notebooks
10 | 2023-05-23 | Finalising Regression results | 2 hours | Yes | Lilia
10 | 2023-05-23 | Adding more markdown info to Income levels dataset | 1 hour | Yes | Emi added more notes to income level dataset
10 | 2023-05-23 | Catch up meeting to go through results | 1 hour | No | Emi, Rhianna, Natalie - went through the reg results and talked about next steps for report
10 | 2023-05-23 | Meeting to go through results | 40 mins | Yes | Emi, Rhianna, Natalie, Lilia - Lilia went through the GPI and regression notebooks
10 | 2023-05-24 | Meeting to go through what's left and next steps | 30mins | Yes | Emi, Rhianna, Natalie, Lilia,Befru- Met to discuss next steps and putting all docs together.
10 | 2023-05-24 | Started working on the Raedme file | 1 hour | No | Emi- started working on the read me file
10 | 2023-05-25 | Continued working on the Readme file | 2 hours | No | Emi- Is working on content for the readme file
10 | 2023-05-26 | sorting out to-be-marked branch | Approximately 2 hours | no | Natalie - Tidied up notebooks and made a new branch which will be marked
10 | 2023-05-26 | Adding to readme | 1:30mins | No | Emi- Readme is potentially done, just need to amend once the new branch has been updated
10 | 2023-05-26 | Meeting to tie up loose ends | 1:50mins | No | Emi, Rhianna and Nat- Met to tie up loose ends and finish the project report
| 2023-05-26 | report writing | 1.5 hrs | No | Natalie - Wrote up results section of report.
10 | 2023-05-27 | Edited the Project Report & Created Roadmap. | 2.5 hours | Yes | Befru - Refined details as needed and wrote the conclusion and created a roadmap of the project, attached it in the report.
10 | 2023-05-27 | Fixed errors in regression notebook, added to Lilia's result input into report, finalised all notebooks and pushed to GitHub | approx. 2 hrs | Yes | Natalie - tidied up bits and pieces, debugging regression notebook,added Lilia's bit to results bit of report, finalised notebooks in final branch.
10 | 2023-05-28 | Submitting | approx 1 hr | Yes | Natalie - Submitted everything to GitHub, finalised readme file
|  | Total time: | 67 hours and 37 minutes
Note on C8: ====== ID#AAAAwogVklY natalie feak (2023-05-10 16:18:39) This was done within the class session, so doesn't count towards our minutes